## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Tester A | 2026-03-16 | NotImplementedError in actions.py | Sprint 2 | Backend Dev | Functional | Added name() method to Action classes. | 2026-03-16 | Closed | Fixed Rasa registration.
2 | Tester B | 2026-03-18 | WinError 10061 Connection Refused | Sprint 3 | Integration | Connectivity | Started FastAPI server on Port 8000. | 2026-03-18 | Closed | Port conflict resolved.
3 | Tester A | 2026-03-20 | AssertionError: No text to speak (gTTS) | Sprint 3 | Voice Lead | Logic/Crash | Added guard clauses for empty strings. | 2026-03-21 | Closed | Prevents system crash.
4 | Tester C | 2026-03-22 | Noise detected as Finnish (fi) | Sprint 3 | AI Lead | NLU/STT | Implemented langdetect filter for 'en','hi','te','ta'. | 2026-03-23 | Closed | Fixed audio drift.
5 | Tester B | 2026-03-25 | OperationalError: No such table call_logs | Sprint 4 | Backend Dev | Database | Initialized CREATE TABLE script in actions.py. | 2026-03-25 | Closed | DB schema updated.
6 | Tester A | 2026-03-27 | Empty response when Rasa intent fails | Sprint 4 | Integration | UI/UX | Added fallback "I didn't catch that" in bridge. | 2026-03-28 | Closed | Improved user experience.

## Sheet2
Sl No | Category | Test Case Description | Expected Result | Actual Result | Status
1 | Logical | If user says "Cardiology", system should map to dept slot. | Slot department = "Cardiology" | Slot department = "Cardiology" | ✅ Pass
2 | Logical | If mandatory slots (Time/Doc) are missing, Rasa should loop. | Bot asks follow-up question. | Bot asks follow-up question. | ✅ Pass
3 | User Interface | Speech-to-Text should recognize "Namaste" and translate to "Hello". | Input converted to English. | Input converted to English. | ✅ Pass
4 | User Interface | Text-to-Speech should play audio in the user's detected language. | Clear audio output in 'hi', 'te', etc. | Clear audio output. | ✅ Pass
5 | Maintainability | Database should store every appointment for future retrieval. | New row in appointments table. | New row in appointments table. | ✅ Pass
6 | Maintainability | Code should be modular (Actions, Voice, Gateway separated). | Easy to update one part without breaking others. | System is modular. | ✅ Pass
7 | Standards | PEP8 Python coding standards and SQL naming conventions. | Clean, readable, documented code. | Code follows standards. | ✅ Pass
8 | Standards | API response time between Voice Bot and Rasa. | Response within 2-3 seconds. | Average 1.8s response. | ✅ Pass
9 | Others | Handle "Refused Connection" if server is down. | User gets "System Offline" message. |  | ✅ Pass